## WBS-Phases-Tasks
Notes | Project Phases and Key Tasks (examples only!) [version 2014-05-14]
PROJECT DEFINITION
Business Assessment / Opportunity Definition
Opportunity Definition
Conceptual Business Process Design (Context Diagram)
High-Level Test Strategy
Agreement to move forward with Scoping/Charter
Define Charter and Scope of Project
Draft Charter
Incorporate Feedback
Submit Final Charter to Executive Sponsors
Approve/Fund Charter
Post Final Charter on BOX (public version on confuence if needed)
PROJECT PLANNING & MANAGEMENT
Establish project identity
Identify internal project resources
Identify external project resources
Prepare project plan draft
Develop project communication plan
Conduct project team kick-off & planning
Develop process to manage scope/control changes
Develop process to measure success
Setup JIRA Projects
Setup Confluence
Setup BOX (asdocs area)
Setup Timeweb / Unanet
Provide Document Templates as needed
Identify project business and technical risks
Internal Project review
User acceptance/project review
Onboard Staff as planned for Requirements phase
Ongoing Project Management
Review and Outline Key Plans (what? and owners?)
QA High-Level Plan & Proposal for UAT
Information Security Office Questionnaire
Campus Readiness Plan
Cutover Plan Outline
REQUIREMENTS DEFINITION PHASE
Identify and prepare Working Group team
Schedule Working Group Meetings
Conduct Working Group Meetings
Business Process Analysis (for each functionality area)
Prepare interview questionnaires/approach
Conduct interviews / analysis sessions
Publish Working Group write-ups and incorporate feedback
Draft BRD for each functionality/ deliverable area
Review for Training (CAE) Impact Assessment
Review Draft BRD - Working Group
Review Draft BRD - AS Team (QA, Tech Lead, PM)
Incorporate any needed changes
Final BRD Review
BRD Sign-off
DESIGN PHASE
Environment Planning, document on confluence
Development
SIT/QA Test
UAT Test
Confirm environment for End-2-End Testing
Sandbox, Test Area for Training Development
Provide templates to BA's and team
Functional Design Specifications
Business Process Design (Flows)
Draft Business Process Design
Review with Working Group
Incorporate feedback
Sign-off Business Process Design
Application Design (UI Mock-ups, Use Cases, Prototype)
Draft application Functional Designs
Review with Working Group
Incorporate feedback
Sign-off Application Functional Designs
Data Conversion, Migration Design
Draft data conversion/migration specification
Draft data conversion/migration mapping details
Review with Working Group
Incorporate feedback
Sign-off Conversion-Migration Functional Design
Reports Design (operational, ad hoc, other)
Draft Report Functional Designs (mock-ups, specs)
Review with Working Group
Incorporate feedback
Sign-off Report Functional Design
Access & Security Design
Draft Access & Security Functional Design
Review with Working Group
Incorporate feedback
Sign-off Access-Security Functional Design
Data Base Conceptual Design
Draft Data Base Conceptual Design
Review with Working Group
Incorporate feedback
Sign-off Access-Security Functional Design
Interface, Integration Logical Design
Draft Interface Functional Design
Review with Working Group
Incorporate feedback
Sign-off Interface-Integration Functional Design
IT infrastructure / technology summary, document
Publish Design Documents to repository (BOX, Confluence)
Functional Designs Completed - Milestone
Technical Design Specifications
Application Design (UI, Flows, other)
Dev Intake
Draft application Tech Design Specs
Review with Tech Team/Reviewers
Incorporate feedback
Sign-off Application Tech Design Specifications
Data Conversion, Migration Tech Design
Dev Intake
Draft data conversion/migration process
Review with Tech Team/Reviewers
Incorporate feedback
Sign-off conversion/migration Tech Design Specifications
Reports Design (platform specific specs)
Dev Intake
Draft Report Tech Designs Specs
Review with Tech Team/Reviewers
Incorporate feedback
Sign-off Reports Tech Design Specifications
Access & Security Design
Dev Intake
Draft Access (authority)/Security Design Specifications
Review with Tech Team/Reviewers
Incorporate feedback
Sign-off Access/Security Tech Design Specifications
Configuration Design
Dev Intake
Draft Configuration Tech Design Specifications
Review with Tech Team/Reviewers
Incorporate feedback
Sign-off Configuration Tech Design Specifications
Data Base Technical Design
Dev Intake
Draft Data Base Tech Design Specifications
Review with Tech Team/Reviewers
Incorporate feedback
Sign-off Configuration Tech Design Specifications
Interface, Integration Design
Dev Intake
Draft Integration/Interface Tech Design Specifications
Review with Tech Team/Reviewers
Incorporate feedback
Sign-off Interface/Integration Tech Design Specifications
IT infrastructure / technology plan
Publish technical design documents to repository (BOC, Confluence)
Technical Designs Completed - Milestone
DEVELOPMENT / CONSTRUCTION
Data Base Development
Dev Intake
Build Data Base, Provide Access
Code reviews
Unit Test, Rework
Application Development (UI, Flows, other)
Dev Intake
Develop Application Components per design
Code review
Unit Test, Rework
Data Conversion, Migration Development
Dev Intake
Develop data conversion code/scripts per design
Code review
Unit Test, Rework
Reports Development
Dev Intake
Develop Reports per design
Review prototypes with Tech Team
Unit Test, Rework
Access & Security Implementation
Dev Intake
Develop, Set Up, Configure Authority/Security Components
Unit Test, Rework
Configuration Development
Dev Intake
Implement Configuration/Setup per design
Review with Tech Team
Unit Test, Rework
Interface, Integration Design
Dev Intake
Develop Interface, Integration components per design
Code review
Unit Test, Rework
IT infrastructure / technology summary, document
Development/Construction Complete - Milestone
SIT/QA PLANNING
Develop Testing Strategy Document
Review Testing Strategy Draft with Project Team
Incorporate Feedback
Finalize Test Strategy to Confluence
Develop Test Plan for new functionality
Develop Test Plan for existing functionality (regression)
Develop Test Plan for data conversion/migration
Develop Performance and Load Test Plan
Develop Test Cases and Test Scripts
Team review and finalize test plans and test cases
Post Test Cases in Zephyr
Set up Jira for SIT/QA
Prepare SIT/QA Exit Criteria
SIT Environment Preparation
Confirm environments (PeopleSoft, Oracle, Apex, EDW)
Coordinate/confirm refresh schedules for data sources/targets
Confirm interface dependencies for end-2-end testing
Set up access (db, application, webauth, reporting)
Notify infrastructure support of SIT testing schedule
SIT/QA TESTING
Deployment for SIT/QA testing
SIT Environment Validation
Readiness confirmation from tech team
BA review of key functionality prior to turnover to QA
Determine any known issues
First Pass Testing
Conversion/Migration Testing
Application Testing
Reports Testing, Reconciliation
Bug Fixes
Retesting Fixes, Resolution
End-2-End, Integration Testing
SIT/QA Exit Criteria Completed & Approved - Milestone
UAT PLANNING
Create list of Business Users/Testers
Create UAT Test Plan Document
Finalize and Approve UAT Plan
Communicate UAT Plans to Users
Create UAT Test Cases / Scripts
Train Users as needed to create test scripts/cases
Schedule Rooms for UAT Test Sessions
Create Email Dist. Lists for UAT (Core Team, Extended)
Prepare UAT Exit Criteria
UAT Environment Preparation
Confirm environments (PeopleSoft, Oracle, Apex, EDW)
Coordinate/confirm refresh schedules for data sources/targets
Confirm interface dependencies for end-2-end testing
Set up Authority Manager access as needed (imports, integration)
Set up access (db, application, webauth, reporting)
Notify infrastructure support of UAT testing schedule
CRP TESTING (Conference Room Pilot)
Create Test Scenarios (as needed)
Schedule Testing Sessions
Conduct Testing Sessions
Capture Results, Review and Prioritize as needed
UAT TEST EXECUTION
System Deployment For UAT Testing
UAT Environment Validation
Readiness confirmation from tech team
BA review of key functionality prior to UAT sessions
Determine any known issues
First Pass Testing
Authority & Security Testing
Application Testing, Business Functions
Configuration Testing
Data Conversion / Migration Testing
End-2-End, Integration Testing
User Community Testing
Load Testing
Performance Testing
Bug Fixes
Retesting Fixes, Resolution
Test Results Publish on Confluence
UAT Exit Criteria Completed & Approved - Milestone
CAE / READINESS (Training, Communications, Cust. Support)
Analysis & Design
Define target users, roles & tasks -Ad-hoc
Develop Change Management Plan
Develop Training Plan
Draft Training Design Doc
Schedule Training Facilities & Equipment
Develop Communication Plan
Develop Support Plan
Development / Training
Develop Training Materials
Develop Online Web Support Materials
Implement Communication Plan Deliverables
Training Enrollment Email / Communication
Post Training Email & Survey
Survey Results / Communication
Prepare Client Support Infrastructure
Design Remedy Workflow / JIRA Queues
Update Knowledge Base
Implementation / Communication
Implement time-phased communication plan
Set-up course in STARS for enrollment
Print training materials (user guide, exercises)
Release online web support materials
Pilot Training Class
Deliver Training
Implement client support infrastructure
Evaluation / Customer Support
Develop Course Survey
Distribute Course Survey
Compile/Report Survey Results
Compile and report usage stats
ROLLOUT (Pilot or Full Production)
Move to Production Checklist
Authority & Security Setup
PCR Ticket and PCR Meeting
System Readiness Review
Approval to Deploy, Development Team
Approval to Deploy, Business Owners
Deploy Application to Production
Production Verification by SME's, BA's, Tech Lead, QA
GO-LIVE
Communicate Go-Live to User Community and Project Team
Go-Live Support
Note on A2: Author: NOTE to READERS: The tasks and deliverables included in this template are examples only and intended to outline some of the common activities/deliverables required software application projects. Many of the areas may need to be tailored for platform specific needs, e.g. a Data Warehouse / Reporting solution will have different design, development elements than a PeopleSoft application.
Note on A12: Author: Schedule meeting with Randy, Noel, Management for approval review. Note: Some projects may have separate Requirements and Implementation Charters. In these cases, funding will typically be requested as part of the Implementation Charter. The Requirements phase charter may also need to be reviewed and approved with Randy, Noel and executive management.
Note on A13: Author: Post the final charter to the AS Charters folder in BOX. Public version has FINANCIAL $$ amounts removed; for charters posted on Confluence.
Note on A27: Author: Documents may include: - Business Requirements Definition (BRD) - Mockup tools/standards - Layout / Mockup spreadsheets - Mapping documents - Authority Manager/Security Definition templates - Confluence templates - Application specific templates (e.g. OBI, Oracle, PeopleSoft)
Note on A34: Author: - Creating a test plan/outline early will help identify gaps or areas in remaining phases that need to be addressed.
Note on A35: Author: - Ensure that current security practices are documented and in compliance (or planned) for the solution design.
Note on A36: Author: - Includes Training & Communications - Client Advocacy Activities - Owners for this area
Note on A38: Author: Requirements Definition Phase - Create the BRD This is the "What" the customer wants
Note on A52: Author: Sign-off / approval done by stakeholders as designated in the roles and responsibilities of the project charter. Note: Some projects may have separate Requirements and Implementation Charters. In these cases, funding will typically be requested as part of the Implementation Charter.
Note on A53: Author: Define "How" the solution will be implemented. Functional & Technical Design Specification deliverables will depend to some extent on the target platform and type of solution, e.g. Oracle, PeopleSoft, Apex, OBIEE, EDW. The information/tasks outline here are just capturing some of the basic / common areas and elements related to a software application project.
Note on B53: Author: Functional & Technical Design Specification deliverables will depend to some extent on the target platform and type of solution, e.g. Oracle, PeopleSoft, Apex, OBIEE, EDW. The information/tasks outline here are just capturing some of the basic / common areas and elements related to a software application project.
Note on A61: Author: Working Group: Placeholder for BA's, SME's, or working group participants tasked with the functional design of the solution.
Note on A104: Author: Dev Intake: this is the date that this activity is started - Tech resource needs to review and acknowledge that this is the correct start-date for the deliverable.
Note on A149: Author: Deliverables/Tasks in this section should come from the tech team; the items noted here are examples only.
Note on A151: Author: Dev Intake: this is the date that this activity is started - Tech resource needs to review and acknowledge that this is the correct start-date for the deliverable.
Note on A261: Author: Example Tasks Only: Client Advocacy and Education (CAE) / Readiness: List of common activities and phases for CAE on the project. CAE team should provide this section as part of planning. CAE needs to be involved early on and throughout the project development.

## WBS-Samples
# | Example WBS:
1 | Sequential Example - some overlap where feasible
2 | Iterations in design (prototypes) and development could be defined in the respective Tech design, Development sections.
3 | Durations: Phase durations shown here are just examples and not meant to define standard % of project time or recommended durations.