## Project Resource Plan Template
Only input data where there is blue colored font! (everything else is a formula)
Role | Employee Type | Assigned To | Allocation % | Start Date | End Date | Actual Working Days | Planned Working Days | Annual Salary | Rate/hr | Budget | Planned Value | Comments
UIT
Project Manager | Full Time | Walter White | 50% | 2015-06-01 | 2016-08-25 | 280 | 324 | 0 | 0 | 0 | 0 | Walt is on operating budget so we ignore his salary.
Business Analyst | Full Time | Jesse Pinkman | 100% | 2015-06-01 | 2016-08-25 | 280 | 324 | 130000 | 62.5 | 226800 | 196000 | Jesse is a fixed term person we hired specifically for this project so his salary is included; at burdened rate.
Data Warehouse Developer | Contractor | Saul Goodman | 100% | 2015-06-01 | 2016-08-25 | 280 | 324 | 180000 | 90 | 233280 | 201600
OBI Developer | Contractor | Mike Ehrmantraut | 100% | 2015-06-01 | 2016-08-25 | 280 | 324 | 180000 | 90 | 233280 | 201600
UIT Subtotal | [9 empty] | 693360 | 599200
Business Office
Program Manager | Full Time | Skyler White | 20% | 2015-06-01 | 2016-08-25 | 280 | 324 | 250000 | 120.1923 | 87231 | 75385 | Ms. White is a fixed term person that the client wanted 20% allocated to this project so her salary is included; at burdened rate. And her allocation % reflects that 20%.
Business Analyst | Full Time | Hank Schrader | 100% | 2015-06-01 | 2016-08-25 | 280 | 324 | 200000 | 96.1538 | 348923 | 301538 | Hank is a fixed term person we hired specifically for this project so his salary is included; at burdened rate.
CAE Analyst | Contractor | Tuco Salamanca | 100% | 2015-06-01 | 2016-08-25 | 280 | 324 | 140000 | 70 | 181440 | 156800 | Tuco is, obviously, a contractor.
Business Office Subtotal | [9 empty] | 617594 | 533723
One-Time Costs | [11 empty] | Since only you, as PM know when these costs might be incurred, please plug the total number in (you can add multiple lines if need be) for both planned total and planned spend to date.
Consultant | [9 empty] | 300000 | 150000
Hardware | [9 empty] | 200000 | 75000
Software License | [9 empty] | 100000 | 50000
One-Time Costs Subtotal | [9 empty] | 300000 | 125000
TOTAL | [9 empty] | 1610954 | 1257923 | <<<< Plug these numbers into the Project Info line in the 'Project Base Budget' and 'Planned Value' columns, respectively, in your project plan monthly!
Formulas:
Actual Working Days = NETWORKDAYS([Start Date],TODAY())
Planned Working Days = NETWORKDAYS([Start Date],[End Date])
Planned Value = ROUND(IF(TODAY()-[Start Date]< 0, 0, IF([Actual Working Days]>[Planned Working Days], [Budget], [Actual Working Days]/[Planned Working Days]*[Budget])),0)

## Dropdown Values
Full Time
Contractor